## Report Data
Project Name | Vendor Name | Total Budget | Current Status | Milestone Name | Milestone Status | Planned Delivery Date | Actual Delivery Date | Payment Amount
Project Alpha - ERP Migration | CloudNine Solutions | 450000 | Active | Phase 1 - Discovery & Audit | Completed | 2025-04-01 | 2025-04-05 | 50000
Project Alpha - ERP Migration | CloudNine Solutions | 450000 | Active | Phase 2 - Data Migration | In-Progress | 2025-05-15 |  | 120000
Project Alpha - ERP Migration | CloudNine Solutions | 450000 | Active | Phase 3 - Integration Testing | Pending | 2025-07-01 |  | 100000
Project Alpha - ERP Migration | CloudNine Solutions | 450000 | Active | Phase 4 - Go-Live & Handoff | Pending | 2025-09-01 |  | 180000
Project Delta - Security Audit | SecureNet Inc. | 120000 | Completed | Final Compliance Sign-off | Completed | 2024-09-30 | 2024-09-28 | 30000
Project Delta - Security Audit | SecureNet Inc. | 120000 | Completed | M3 – Compliance Evidence Package | Completed | 2024-12-15 | 2024-12-10 | 50000
Project Delta - Security Audit | SecureNet Inc. | 120000 | Completed | Remediation Implementation | Delayed | 2024-08-30 | 2024-09-05 | 50000
Project Delta - Security Audit | SecureNet Inc. | 120000 | Completed | Security Assessment Report | Completed | 2024-07-15 | 2024-07-10 | 40000